## Sprint Backlog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Virtual TA: Frontend Development and Integration>
SB4/US1 | As a Developer, I want to design the frontend architecture so that the UI is well-structured. | SB4/US1/T1 | HC: Research frontend frameworks and design patterns | HC | Not Started | 2025-12-01
|  | SB4/US1/T2 | HC: Create wireframes for the Virtual TA interface | HC | Not Started | 2025-12-02
|  | SB4/US1/T3 | HC: Define component structure and layout | HC | Not Started | 2025-12-03
SB4/US2 | As a Developer, I want to create the HTML structure so that the UI has proper semantic markup. | SB4/US2/T1 | HC: Create index.html with semantic HTML5 | HC | Not Started | 2025-12-04
|  | SB4/US2/T2 | HC: Add form elements for question input | HC | Not Started | 2025-12-05
|  | SB4/US2/T3 | HC: Add file upload component for image support | HC | Not Started | 2025-12-06
SB4/US3 | As a Developer, I want to implement CSS styling so that the interface is visually appealing. | SB4/US3/T1 | HC: Create responsive layout with CSS Grid/Flexbox | HC | Not Started | 2025-12-07
|  | SB4/US3/T2 | HC: Design color scheme and typography | HC | Not Started | 2025-12-08
|  | SB4/US3/T3 | HC: Add animations and transitions for better UX | HC | Not Started | 2025-12-09
SB4/US4 | As a Developer, I want to implement JavaScript functionality so that the frontend interacts with the API. | SB4/US4/T1 | HC: Create API client for Virtual TA endpoint | HC | Not Started | 2025-12-10
|  | SB4/US4/T2 | HC: Implement form submission handler | HC | Not Started | 2025-12-11
|  | SB4/US4/T3 | HC: Add image encoding for base64 conversion | HC | Not Started | 2025-12-12
SB4/US5 | As a User, I want to submit questions so that I can get answers from the Virtual TA. | SB4/US5/T1 | HC: Create question input field with validation | HC | Not Started | 2025-12-13
|  | SB4/US5/T2 | HC: Implement submit button and keyboard shortcuts | HC | Not Started | 2025-12-14
|  | SB4/US5/T3 | HC: Add loading indicator during API calls | HC | Not Started | 2025-12-15
SB4/US6 | As a User, I want to upload images so that the TA can analyze screenshots. | SB4/US6/T1 | HC: Implement drag-and-drop image upload | HC | Not Started | 2025-12-16
|  | SB4/US6/T2 | HC: Add image preview functionality | HC | Not Started | 2025-12-17
|  | SB4/US6/T3 | HC: Validate image file types and size | HC | Not Started | 2025-12-18
SB4/US7 | As a User, I want to view answers so that I can get information from the Virtual TA. | SB4/US7/T1 | HC: Create answer display component | HC | Not Started | 2025-12-19
|  | SB4/US7/T2 | HC: Format and render markdown/rich text | HC | Not Started | 2025-12-20
|  | SB4/US7/T3 | HC: Display source links with click handlers | HC | Not Started | 2025-12-21
SB4/US8 | As a Developer, I want to implement error handling so that users get helpful feedback. | SB4/US8/T1 | HC: Add try-catch blocks for API calls | HC | Not Started | 2025-12-22
|  | SB4/US8/T2 | HC: Display user-friendly error messages | HC | Not Started | 2025-12-23
|  | SB4/US8/T3 | HC: Implement retry mechanism for failed requests | HC | Not Started | 2025-12-24
SB4/US9 | As a Developer, I want to add CORS support so that the API works with the frontend. | SB4/US9/T1 | HC: Verify CORS configuration in API | HC | Not Started | 2025-12-25
|  | SB4/US9/T2 | HC: Test cross-origin requests | HC | Not Started | 2025-12-26
|  | SB4/US9/T3 | HC: Handle CORS-related errors gracefully | HC | Not Started | 2025-12-27
SB4/US10 | As a Developer, I want to create a chat history feature so that users can review past queries. | SB4/US10/T1 | HC: Implement local storage for chat history | HC | Not Started | 2025-12-28
|  | SB4/US10/T2 | HC: Create UI to display conversation history | HC | Not Started | 2025-12-29
|  | SB4/US10/T3 | HC: Add clear history functionality | HC | Not Started | 2025-12-30
SB4/US11 | As a User, I want the interface to be responsive so that I can use it on mobile devices. | SB4/US11/T1 | HC: Implement mobile-first responsive design | HC | Not Started | 2025-12-31
|  | SB4/US11/T2 | HC: Test on various screen sizes | HC | Not Started | 2026-01-01
|  | SB4/US11/T3 | HC: Optimize touch interactions for mobile | HC | Not Started | 2026-01-02
SB4/US12 | As a Developer, I want to optimize performance so that the app loads quickly. | SB4/US12/T1 | HC: Minify CSS and JavaScript files | HC | Not Started | 2026-01-03
|  | SB4/US12/T2 | HC: Optimize images and assets | HC | Not Started | 2026-01-04
|  | SB4/US12/T3 | HC: Implement lazy loading where appropriate | HC | Not Started | 2026-01-05
SB4/US13 | As a Developer, I want to add accessibility features so that the app is usable by everyone. | SB4/US13/T1 | HC: Add ARIA labels and semantic HTML | HC | Not Started | 2026-01-06
|  | SB4/US13/T2 | HC: Ensure keyboard navigation works | HC | Not Started | 2026-01-07
|  | SB4/US13/T3 | HC: Test with screen readers | HC | Not Started | 2026-01-08
SB4/US14 | As a Developer, I want to create frontend documentation so that others can understand the code. | SB4/US14/T1 | HC: Document component structure and architecture | HC | Not Started | 2026-01-09
|  | SB4/US14/T2 | HC: Add code comments for complex functions | HC | Not Started | 2026-01-10
|  | SB4/US14/T3 | HC: Create README for frontend setup | HC | Not Started | 2026-01-11
SB4/US15 | As a Developer, I want to test the frontend so that bugs are caught early. | SB4/US15/T1 | HC: Perform manual testing of all features | HC | Not Started | 2026-01-12
|  | SB4/US15/T2 | HC: Test with different browsers | HC | Not Started | 2026-01-13
|  | SB4/US15/T3 | HC: Fix identified bugs and issues | HC | Not Started | 2026-01-14
SB4/US16 | As a Developer, I want to deploy the frontend so that users can access it. | SB4/US16/T1 | HC: Choose hosting platform for static files | HC | Not Started | 2026-01-15
|  | SB4/US16/T2 | HC: Configure deployment settings | HC | Not Started | 2026-01-16
|  | SB4/US16/T3 | HC: Deploy frontend and verify functionality | HC | Not Started | 2026-01-17
SB4/US17 | As a Developer, I want to add theme support so that users can customize appearance. | SB4/US17/T1 | HC: Implement light/dark theme toggle | HC | Not Started | 2026-01-18
|  | SB4/US17/T2 | HC: Create CSS variables for theming | HC | Not Started | 2026-01-19
|  | SB4/US17/T3 | HC: Save theme preference to local storage | HC | Not Started | 2026-01-20
SB4/US18 | As a Developer, I want to integrate API endpoint so that frontend can communicate with backend. | SB4/US18/T1 | HC: Configure API endpoint URL | HC | Not Started | 2026-01-21
|  | SB4/US18/T2 | HC: Test API connectivity | HC | Not Started | 2026-01-22
|  | SB4/US18/T3 | HC: Handle API authentication if required | HC | Not Started | 2026-01-23
SB4/US19 | As a User, I want to see example queries so that I know what to ask. | SB4/US19/T1 | HC: Create list of sample questions | HC | Not Started | 2026-01-24
|  | SB4/US19/T2 | HC: Add quick action buttons for examples | HC | Not Started | 2026-01-25
|  | SB4/US19/T3 | HC: Implement auto-fill on example click | HC | Not Started | 2026-01-26
SB4/US20 | As a Developer, I want to add analytics tracking so that usage can be monitored. | SB4/US20/T1 | HC: Implement basic analytics tracking | HC | Not Started | 2026-01-27
|  | SB4/US20/T2 | HC: Track user interactions and queries | HC | Not Started | 2026-01-28
|  | SB4/US20/T3 | HC: Create dashboard for monitoring (optional) | HC | Not Started | 2026-01-29
SB4/US21 | As a Developer, I want to create a landing page so that users understand the Virtual TA. | SB4/US21/T1 | HC: Design landing page layout | HC | Not Started | 2026-01-30
|  | SB4/US21/T2 | HC: Add project description and features | HC | Not Started | 2026-01-31
|  | SB4/US21/T3 | HC: Create call-to-action elements | HC | Not Started | 2026-02-01
SB4/US22 | As a Developer, I want to add loading animations so that users know the app is working. | SB4/US22/T1 | HC: Create loading spinner component | HC | Not Started | 2026-02-02
|  | SB4/US22/T2 | HC: Add skeleton screens for content loading | HC | Not Started | 2026-02-03
|  | SB4/US22/T3 | HC: Implement smooth transitions | HC | Not Started | 2026-02-04
SB4/US23 | As a User, I want to copy answers so that I can save useful information. | SB4/US23/T1 | HC: Add copy-to-clipboard button | HC | Not Started | 2026-02-05
|  | SB4/US23/T2 | HC: Show confirmation on successful copy | HC | Not Started | 2026-02-06
|  | SB4/US23/T3 | HC: Format copied text appropriately | HC | Not Started | 2026-02-07
SB4/US24 | As a Developer, I want to implement rate limiting so that API is not overwhelmed. | SB4/US24/T1 | HC: Add client-side rate limiting | HC | Not Started | 2026-02-08
|  | SB4/US24/T2 | HC: Display rate limit warnings | HC | Not Started | 2026-02-09
|  | SB4/US24/T3 | HC: Queue requests if needed | HC | Not Started | 2026-02-10
SB4/US25 | As a Developer, I want to add final polish so that the frontend is production-ready. | SB4/US25/T1 | HC: Review and refactor code | HC | Not Started | 2026-02-11
|  | SB4/US25/T2 | HC: Optimize bundle size | HC | Not Started | 2026-02-12
|  | SB4/US25/T3 | HC: Perform final testing and deployment | HC | Not Started | 2026-02-13
SB4/US26 | As a Developer, I want to update project documentation so that Sprint 4 work is captured. | SB4/US26/T1 | HC: Update README with frontend information | HC | Not Started | 2026-02-14
|  | SB4/US26/T2 | HC: Add deployment instructions | HC | Not Started | 2026-02-15
|  | SB4/US26/T3 | HC: Document API usage from frontend perspective | HC | Not Started | 2026-02-16
SB4/US27 | As a Developer, I want to create user guide so that users know how to use the Virtual TA. | SB4/US27/T1 | HC: Write step-by-step usage guide | HC | Not Started | 2026-02-17
|  | SB4/US27/T2 | HC: Add screenshots and examples | HC | Not Started | 2026-02-18
|  | SB4/US27/T3 | HC: Include troubleshooting section | HC | Not Started | 2026-02-19
SB4/US28 | As a Developer, I want to implement feedback mechanism so that users can report issues. | SB4/US28/T1 | HC: Add feedback form or link | HC | Not Started | 2026-02-20
|  | SB4/US28/T2 | HC: Create issue template for bug reports | HC | Not Started | 2026-02-21
|  | SB4/US28/T3 | HC: Set up notification system for feedback | HC | Not Started | 2026-02-22
SB4/US29 | As a Developer, I want to configure CI/CD so that frontend deploys automatically. | SB4/US29/T1 | HC: Set up GitHub Actions for frontend | HC | Not Started | 2026-02-23
|  | SB4/US29/T2 | HC: Configure automatic deployment | HC | Not Started | 2026-02-24
|  | SB4/US29/T3 | HC: Add build and test steps to pipeline | HC | Not Started | 2026-02-25
SB4/US30 | As a Developer, I want to conduct final review so that Sprint 4 is complete. | SB4/US30/T1 | HC: Review all deliverables | HC | Not Started | 2026-02-26
|  | SB4/US30/T2 | HC: Ensure all acceptance criteria are met | HC | Not Started | 2026-02-27
|  | SB4/US30/T3 | HC: Prepare Sprint 4 retrospective notes | HC | Not Started | 2026-02-28

## SB BD Ch04
Sprint Backlog 04 burn down chart
Date | Planned Total Task | Actual Incomplete Task
2025-12-01 | 90 | 90
2025-12-02 | 87.6 | 87.6
2025-12-03 | 85.1 | 85.1
2025-12-04 | 82.7 | 82.7
2025-12-05 | 80.3 | 80.3
2025-12-06 | 77.8 | 77.8
2025-12-07 | 75.4 | 75.4
2025-12-08 | 73 | 73
2025-12-09 | 70.5 | 70.5
2025-12-10 | 68.1 | 68.1
2025-12-11 | 65.7 | 65.7
2025-12-12 | 63.2 | 63.2
2025-12-13 | 60.8 | 60.8
2025-12-14 | 58.4 | 58.4
2025-12-15 | 55.9 | 55.9
2025-12-16 | 53.5 | 53.5
2025-12-17 | 51.1 | 51.1
2025-12-18 | 48.6 | 48.6
2025-12-19 | 46.2 | 46.2
2025-12-20 | 43.8 | 43.8
2025-12-21 | 41.4 | 41.4
2025-12-22 | 38.9 | 38.9
2025-12-23 | 36.5 | 36.5
2025-12-24 | 34.1 | 34.1
2025-12-25 | 31.6 | 31.6
2025-12-26 | 29.2 | 29.2
2025-12-27 | 26.8 | 26.8
2025-12-28 | 24.3 | 24.3
2025-12-29 | 21.9 | 21.9
2025-12-30 | 19.5 | 19.5
2025-12-31 | 17 | 17
2026-01-01 | 14.6 | 14.6
2026-01-02 | 12.2 | 12.2
2026-01-03 | 9.7 | 9.7
2026-01-04 | 7.3 | 7.3
2026-01-05 | 4.9 | 4.9
2026-01-06 | 2.4 | 2.4
2026-01-07 | 0 | 0