## Product Backlog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT |  |  |  |  | Student Name | Code
1 | SB1/US1 | Developer | Set up the project repository and environment | the team can collaborate effectively | 1 | Team Lead | 2025-01-15 |  | Harsh Choudhary | HC
1 | SB1/US2 | Developer | Create scripts to scrape course content from TDS website | we can build the knowledge base with course materials | 1 | Developer 1 | 2025-01-17 |  | Developer A | DA
1 | SB1/US3 | Developer | Create scripts to scrape Discourse forum posts | we can include forum discussions in the knowledge base | 1 | Developer 2 | 2025-01-18 |  | Developer B | DB
1 | SB1/US4 | Developer | Implement date range filtering for Discourse posts | we can scrape posts from specific time periods | 2 | Developer 2 | 2025-01-19 |  | Developer B | DB
1 | SB1/US5 | Developer | Test and validate scraped data quality | we ensure accurate data for the knowledge base | 1 | QA Lead | 2025-01-20 |  | Tester C | TC
2 | SB2/US1 | Developer | Design the SQLite database schema for the knowledge base | we can store course and forum data efficiently | 1 | Developer 1 | 2025-01-22 |  | Developer A | DA
2 | SB2/US2 | Developer | Implement text chunking functionality | we can break down long documents into manageable pieces | 1 | Developer 1 | 2025-01-23 |  | Developer A | DA
2 | SB2/US3 | Developer | Integrate SentenceTransformer for local embeddings | we can generate embeddings without external API dependencies | 1 | Developer 2 | 2025-01-24 |  | Developer B | DB
2 | SB2/US4 | Developer | Create knowledge base creation script | we can populate the database with chunked and embedded content | 1 | Developer 1 | 2025-01-25 |  | Developer A | DA
2 | SB2/US5 | Developer | Implement URL update functionality for Discourse links | all forum links work correctly | 2 | Developer 2 | 2025-01-26 |  | Developer B | DB
2 | SB2/US6 | Developer | Test embedding quality and retrieval accuracy | we ensure relevant content is retrieved for queries | 1 | QA Lead | 2025-01-27 |  | Tester C | TC
3 | SB3/US1 | Developer | Create FastAPI application structure | we can build the REST API for the Virtual TA | 1 | Developer 1 | 2025-01-29 |  | Developer A | DA
3 | SB3/US2 | Developer | Implement semantic search with embeddings | users can get relevant answers based on their questions | 1 | Developer 1 | 2025-01-30 |  | Developer A | DA
3 | SB3/US3 | Developer | Integrate OCR capability for image processing | users can ask questions with screenshots | 2 | Developer 2 | 2025-01-31 |  | Developer B | DB
3 | SB3/US4 | Developer | Implement LLM integration for answer generation | the system provides coherent answers with proper citations | 1 | Developer 1 | 2025-02-01 |  | Developer A | DA
3 | SB3/US5 | Developer | Add CORS middleware and security features | the API is secure and accessible from web applications | 1 | Developer 2 | 2025-02-02 |  | Developer B | DB
3 | SB3/US6 | Developer | Implement logging and error handling | we can monitor and debug the application effectively | 2 | Developer 2 | 2025-02-03 |  | Developer B | DB
3 | SB3/US7 | User | Query the Virtual TA with text questions | I can get answers from course materials and forums | 1 | Developer 1 | 2025-02-04 |  | Developer A | DA
3 | SB3/US8 | User | Include images in my questions | I can get help with visual content like diagrams | 2 | Developer 2 | 2025-02-04 |  | Developer B | DB
4 | SB4/US1 | Developer | Create Dockerfile for containerization | the application can be deployed easily | 1 | DevOps Lead | 2025-02-06 |  | DevOps D | DD
4 | SB4/US2 | Developer | Set up deployment on Render/Cloud platform | the Virtual TA is accessible to students | 1 | DevOps Lead | 2025-02-08 |  | DevOps D | DD
4 | SB4/US3 | Developer | Implement comprehensive API testing | all endpoints work correctly | 1 | QA Lead | 2025-02-09 |  | Tester C | TC
4 | SB4/US4 | User | Access the Virtual TA through a web interface | I can easily ask questions without technical knowledge | 2 | Developer 1 | 2025-02-10 |  | Developer A | DA
4 | SB4/US5 | Developer | Create comprehensive documentation | users and developers understand how to use and maintain the system | 1 | Tech Writer | 2025-02-11 |  | Writer E | WE
4 | SB4/US6 | Developer | Monitor and optimize performance | the system responds quickly to user queries | 2 | DevOps Lead | 2025-02-12 |  | DevOps D | DD