## Sprint Backlog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Virtual TA: Project Setup and Data Scraping>
SB1/US1 | As a Developer, I want to set up the project repository and environment so that the team can collaborate effectively. | SB1/US1/T1 | HC: Create GitHub repository and initialize README | HC | Completed | 2025-01-15
|  | SB1/US1/T2 | HC: Set up Python virtual environment and install initial dependencies | HC | Completed | 2025-01-15
|  | SB1/US1/T3 | HC: Create .gitignore file for Python project | HC | Completed | 2025-01-15
|  | SB1/US1/T4 | Team: Review project structure and confirm setup | ALL | Completed | 2025-01-16
SB1/US2 | As a Developer, I want to create scripts to scrape course content from TDS website so that we can build the knowledge base with course materials. | SB1/US2/T1 | DA: Research TDS website structure and scraping requirements | DA | Completed | 2025-01-16
|  | SB1/US2/T2 | DA: Implement website_downloader_full.py script | DA | Completed | 2025-01-17
|  | SB1/US2/T3 | DA: Add HTML to Markdown conversion functionality | DA | Completed | 2025-01-17
|  | SB1/US2/T4 | DA: Test scraping with different course pages | DA | Completed | 2025-01-18
|  | SB1/US2/T5 | DB: Review and optimize scraping code | DB | Completed | 2025-01-18
SB1/US3 | As a Developer, I want to create scripts to scrape Discourse forum posts so that we can include forum discussions in the knowledge base. | SB1/US3/T1 | DB: Study Discourse API documentation | DB | Completed | 2025-01-17
|  | SB1/US3/T2 | DB: Implement discourse_by_date_range.py for date-based scraping | DB | Completed | 2025-01-18
|  | SB1/US3/T3 | DB: Add metadata collection for forum posts | DB | Completed | 2025-01-18
|  | SB1/US3/T4 | DB: Test with different date ranges | DB | Completed | 2025-01-19
SB1/US4 | As a Developer, I want to implement date range filtering for Discourse posts so that we can scrape posts from specific time periods. | SB1/US4/T1 | DB: Create discourse_by_post_id.py for specific post scraping | DB | Completed | 2025-01-19
|  | SB1/US4/T2 | DB: Add post ID validation and error handling | DB | Completed | 2025-01-19
|  | SB1/US4/T3 | DA: Test post ID scraping functionality | DA | Completed | 2025-01-20
SB1/US5 | As a Developer, I want to test and validate scraped data quality so that we ensure accurate data for the knowledge base. | SB1/US5/T1 | TC: Create test cases for scraped data validation | TC | Completed | 2025-01-19
|  | SB1/US5/T2 | TC: Verify course content completeness and accuracy | TC | Completed | 2025-01-20
|  | SB1/US5/T3 | TC: Verify forum posts data structure | TC | Completed | 2025-01-20
|  | SB1/US5/T4 | ALL: Team review of scraped data samples | ALL | Completed | 2025-01-20

## SB BD Ch01
Sprint Backlog 01 burn down chart
Date | Planned Total Task | Actual Incomplete Task
2025-01-15 | 4 | 4
2025-01-16 | 5 | 3
2025-01-17 | 5 | 0
2025-01-18 | 5 | 0
2025-01-19 | 4 | 0
2025-01-20 | 4 | 0