## Sprint Backlog 3
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <JobMirror>
SB3/US1 | As a user, I want to see my live webcam feed so I can see myself. | SB3/US1/T1 | CJ: Integrate react-webcam on Live Interview page. | CJ | Completed | 2025-09-25
|  | SB3/US1/T2 | CJ: Style webcam feed to match UI design. | CJ | Completed | 2025-09-25
|  | SB3/US1/T3 | CY: Test webcam on Chrome and Firefox. | CY | Completed | 2025-09-25
|  | SB3/US1/T4 | HM: Verify webcam component performance. | HM | Completed | 2025-09-25
SB3/US2 | As a user, I want to see the 3D avatar's scene as a placeholder. | SB3/US2/T1 | CJ: Embed Three.js canvas into page layout. | CJ | Completed | 2025-09-26
|  | SB3/US2/T2 | HM: Load basic 3D avatar model into scene. | HM | Completed | 2025-09-26
|  | SB3/US2/T3 | HM: Add idle animation to 3D model. | HM | Completed | 2025-09-26
|  | SB3/US2/T4 | CY: Verify side-by-side layout (webcam + 3D). | CY | Completed | 2025-09-26
SB3/US3 | As a user, I want to see the interview question clearly. | SB3/US3/T1 | CJ: Build QuestionDisplay React component. | CJ | Completed | 2025-09-29
|  | SB3/US3/T2 | CJ: Integrate component into Live Interview UI. | CJ | Completed | 2025-09-29
|  | SB3/US3/T3 | CY: Connect component to /api/questions/random API. | CY | Completed | 2025-09-29
|  | SB3/US3/T4 | HM: Review UI for question readability. | HM | Completed | 2025-09-29
SB3/US4 | As a user, I want "Start," "Pause," and "End" buttons to control the session. | SB3/US4/T1 | CJ: Build SessionControls React component (3 buttons). | CJ | Completed | 2025-09-30
|  | SB3/US4/T2 | CJ: Add SessionControls component to page. | CJ | Completed | 2025-09-30
|  | SB3/US4/T3 | CY: Create dummy functions for button clicks. | CY | Completed | 2025-09-30
|  | SB3/US4/T4 | HM: Test buttons and review console logs. | HM | Completed | 2025-09-30
SB3/US5 | As a dev, I want to create a database entry when an interview starts. | SB3/US5/T1 | CY: Create /api/session/start endpoint. | CY | Completed | 2025-10-01
|  | SB3/US5/T2 | CY: Add logic to create new session doc in Firebase. | CY | Completed | 2025-10-01
|  | SB3/US5/T3 | CJ: Connect "Start" button to call API. | CJ | Completed | 2025-10-01
|  | SB3/US5/T4 | HM: Verify new session doc in Firebase console. | HM | Completed | 2025-10-01
SB3/US6 | As a dev, I want to update the session when an interview ends. | SB3/US6/T1 | CY: Create /api/session/end endpoint. | CY | Completed | 2025-10-02
|  | SB3/US6/T2 | CY: Add logic to update session doc (endTime, status). | CY | Completed | 2025-10-02
|  | SB3/US6/T3 | CJ: Connect "End" button to call API. | CJ | Completed | 2025-10-02
|  | SB3/US6/T4 | HM: Verify session doc update in Firebase console. | HM | Completed | 2025-10-02
SB3/US7 | As an ML engineer, I want to set up MediaPipe for body language analysis. | SB3/US7/T1 | HM: Install MediaPipe JS library in React. | HM | Completed | 2025-10-03
|  | SB3/US7/T2 | HM: Run basic MediaPipe example (hand landmarks). | HM | Completed | 2025-10-03
|  | SB3/US7/T3 | HM: Log raw coordinate data to browser console. | HM | Completed | 2025-10-03
|  | SB3/US7/T4 | CJ: Add "Debug Mode" checkbox to toggle logging. | CJ | Completed | 2025-10-03
SB3/US8 | As an ML engineer, I want to set up the Web Speech API for speech-to-text. | SB3/US8/T1 | HM: Write JS for webkitSpeechRecognition. | HM | Completed | 2025-10-06
|  | SB3/US8/T2 | HM: Add temp "Record" button to test API. | HM | Completed | 2025-10-06
|  | SB3/US8/T3 | HM: Log transcribed text to browser console. | HM | Completed | 2025-10-06
|  | SB3/US8/T4 | CY: Review code and document browser compatibility. | CY | Completed | 2025-10-06
SB3/US9 | As a user, I want the 3D avatar to "speak" the question to me. | SB3/US9/T1 | HM: Write JS for browser's Text-to-Speech (TTS) API. | HM | Completed | 2025-10-07
|  | SB3/US9/T2 | CJ: Create function to speak question text via TTS. | CJ | Completed | 2025-10-07
|  | SB3/US9/T3 | HM: Trigger simple "talking" animation on 3D model. | HM | Completed | 2025-10-07
|  | SB3/US9/T4 | CY: Test speech and animation sync. | CY | Completed | 2025-10-07
SB3/US10 | As a user, I want a loading screen after clicking "Start." | SB3/US10/T1 | CJ: Design a LoadingSpinner component. | CJ | Completed | 2025-10-08
|  | SB3/US10/T2 | CJ: Show spinner after "Start" click, hide on load. | CJ | Completed | 2025-10-08
|  | SB3/US10/T3 | CY: Add simulated 2-second delay for testing. | CY | Completed | 2025-10-08
|  | SB3/US10/T4 | HM: Review the loading experience. | HM | Completed | 2025-10-08
SB3/US11 | As a user, I want to see the report page after clicking "End Interview." | SB3/US11/T1 | CJ: Implement useNavigate from React Router. | CJ | Completed | 2025-10-09
|  | SB3/US11/T2 | CJ: Redirect to /report/:id on "End" API success. | CJ | Completed | 2025-10-09
|  | SB3/US11/T3 | CY: Ensure /api/session/end returns the session ID. | CY | Completed | 2025-10-09
|  | SB3/US11/T4 | HM: Test end-to-end flow (End -> Redirect -> Report). | HM | Completed | 2025-10-09
SB3/US12 | As a user, I want to see my confidence score on the report. | SB3/US12/T1 | CJ: Design a "Score Donut" component. | CJ | Completed | 2025-10-10
|  | SB3/US12/T2 | CJ: Add component to report page UI. | CJ | Completed | 2025-10-10
|  | SB3/US12/T3 | CY: Update /api/report/:id to return mock score. | CY | Completed | 2025-10-10
|  | SB3/US12/T4 | HM: Connect UI to display mock score. | HM | Completed | 2025-10-10
SB3/US13 | As a user, I want to see "Body Language" feedback on the report. | SB3/US13/T1 | CJ: Design FeedbackCard component. | CJ | Completed | 2025-10-13
|  | SB3/US13/T2 | CJ: Add placeholders (Eye Contact, Posture). | CJ | Completed | 2025-10-13
|  | SB3/US13/T3 | CY: Update report API with mock body language data. | CY | Completed | 2025-10-13
|  | SB3/US13/T4 | HM: Define JSON structure for body language data. | HM | Completed | 2025-10-13
SB3/US14 | As a user, I want to see "Voice Analysis" feedback on the report. | SB3/US14/T1 | CJ: Re-use FeedbackCard for voice analysis. | CJ | Completed | 2025-10-14
|  | SB3/US14/T2 | CJ: Add placeholders (Clarity, Pace, Fillers). | CJ | Completed | 2025-10-14
|  | SB3/US14/T3 | CY: Update report API with mock voice data. | CY | Completed | 2025-10-14
|  | SB3/US14/T4 | HM: Define JSON structure for voice data. | HM | Completed | 2025-10-14
SB3/US15 | As a user, I want to see my answers on the report page. | SB3/US15/T1 | CJ: Design "Question & Answer" list component. | CJ | Completed | 2025-10-15
|  | SB3/US15/T2 | CJ: Build component to loop through Q&A array. | CJ | Completed | 2025-10-15
|  | SB3/US15/T3 | CY: Update report API with mock Q&A array. | CY | Completed | 2025-10-15
|  | SB3/US15/T4 | HM: Connect UI to display mock Q&A data. | HM | Completed | 2025-10-15
SB3/US16 | As an ML engineer, I want to prototype "slouch detection." | SB3/US16/T1 | HM: Analyze MediaPipe pose output (shoulders, hips). | HM | Completed | 2025-10-24
|  | SB3/US16/T2 | HM: Write JS function to detect slouching. | HM | Completed | 2025-10-24
|  | SB3/US16/T3 | HM: Log "User is slouching!" to console. | HM | Completed | 2025-10-24
|  | SB3/US16/T4 | CJ: Review logic for future UI alert. | CJ | Completed | 2025-10-24
SB3/US17 | As an ML engineer, I want to prototype a "filler word" counter. | SB3/US17/T1 | HM: Get transcribed text from Web Speech API. | HM | Completed | 2025-10-27
|  | SB3/US17/T2 | HM: Write JS function to count "um," "uh," "like." | HM | Completed | 2025-10-27
|  | SB3/US17/T3 | HM: Log filler word count to console. | HM | Completed | 2025-10-27
|  | SB3/US17/T4 | CY: Review function for saving count to DB. | CY | Completed | 2025-10-27
SB3/US18 | As a dev, I want a WebSocket server for real-time alerts. | SB3/US18/T1 | CY: Install socket.io on Node.js backend. | CY | Completed | 2025-10-28
|  | SB3/US18/T2 | CY: Configure server to listen for connections. | CY | Completed | 2025-10-28
|  | SB3/US18/T3 | CJ: Install socket.io-client in React frontend. | CJ | Completed | 2025-10-28
|  | SB3/US18/T4 | HM: Test connection (server "hello" -> client). | HM | Completed | 2025-10-28
SB3/US19 | As a dev, I want to send a real-time "slouch" alert to the UI. | SB3/US19/T1 | HM: Modify slouch prototype to emit WebSocket message. | HM | In Progress | 2025-10-29
|  | SB3/US19/T2 | CY: Configure WebSocket server to broadcast message. | CY | In Progress | 2025-10-29
|  | SB3/US19/T3 | CJ: Listen for 'slouch_alert' message on frontend. | CJ | In Progress | 2025-10-29
|  | SB3/US19/T4 | CJ: Show a simple alert("You are slouching!"). | CJ | In Progress | 2025-10-29
SB3/US20 | As a user, I want to select an interview type (General, Technical). | SB3/US20/T1 | CJ: Design "Start Interview" modal popup. | CJ | In Progress | 2025-10-30
|  | SB3/US20/T2 | CJ: Add radio buttons for interview types. | CJ | In Progress | 2025-10-30
|  | SB3/US20/T3 | CY: Update /api/session/start to accept interviewType. | CY | In Progress | 2025-10-30
|  | SB3/US20/T4 | HM: Ensure interviewType is saved in Firebase. | HM | In Progress | 2025-10-30
SB3/US21 | As a user, I want the question bank to match the interview type. | SB3/US21/T1 | CY: Categorize questions in question bank JSON. | CY | In Progress | 2025-10-31
|  | SB3/US21/T2 | CY: Modify /api/questions/random to accept type. | CY | In Progress | 2025-10-31
|  | SB3/US21/T3 | CY: Write logic to return question matching type. | CY | In Progress | 2025-10-31
|  | SB3/US21/T4 | CJ: Pass selected type to API when fetching. | CJ | In Progress | 2025-10-31
SB3/US22 | As a dev, I want a UI placeholder for the technical whiteboard. | SB3/US22/T1 | CJ: Design a new Whiteboard component. | CJ | In Progress | 2025-11-03
|  | SB3/US22/T2 | CJ: Add <textarea> as a code editor placeholder. | CJ | In Progress | 2025-11-03
|  | SB3/US22/T3 | CJ: Show Whiteboard only if interviewType is "Technical." | CJ | In Progress | 2025-11-03
|  | SB3/US22/T4 | HM: Review UI and conditional logic. | HM | In Progress | 2025-11-03
SB3/US23 | As a user, I want to see my past interviews on the Dashboard. | SB3/US23/T1 | CJ: Design PastSessionCard component. | CJ | In Progress | 2025-11-04
|  | SB3/US23/T2 | CJ: Call /api/sessions API on Dashboard. | CJ | In Progress | 2025-11-04
|  | SB3/US23/T3 | CY: Ensure API returns all completed sessions. | CY | In Progress | 2025-11-04
|  | SB3/US23/T4 | HM: Test that the list of past interviews displays. | HM | In Progress | 2025-11-04
SB3/US24 | As a user, I want to click a past interview to see its report. | SB3/US24/T1 | CJ: Make each PastSessionCard a clickable link. | CJ | In Progress | 2025-11-05
|  | SB3/US24/T2 | CJ: Link card to /report/:id with correct session ID. | CJ | In Progress | 2025-11-05
|  | SB3/US24/T3 | CY: Test navigation (Dashboard -> Report). | CY | In Progress | 2025-11-05
|  | SB3/US24/T4 | HM: Confirm correct report data is loaded. | HM | In Progress | 2025-11-05
SB3/US25 | As a dev, I want to refine the "About Us" page content. | SB3/US25/T1 | CJ: Improve "About Us" page styling. | CJ | In Progress | 2025-11-06
|  | SB3/US25/T2 | HM: Write paragraph about "Bias Detection." | HM | In Progress | 2025-11-06
|  | SB3/US25/T3 | CY: Write paragraph about technical architecture. | CY | In Progress | 2025-11-06
|  | SB3/US25/T4 | All: Review and approve final page text. | HM+CY+CJ | In Progress | 2025-11-06
SB3/US26 | As a dev, I want to refine the Footer with useful links. | SB3/US26/T1 | CJ: Add "Home," "Dashboard," "About Us" links to Footer. | CJ | In Progress | 2025-11-07
|  | SB3/US26/T2 | HM: Add "Project GitHub" link to footer. | HM | In Progress | 2025-11-07
|  | SB3/US26/T3 | CY: Make footer "sticky" (stays at bottom). | CY | In Progress | 2025-11-07
|  | SB3/US26/T4 | All: Test footer links on all pages. | HM+CY+CJ | In Progress | 2025-11-07
SB3/US27 | As an ML engineer, I want to research "Bias Detection." | SB3/US27/T1 | HM: Research models for text bias detection. | HM | In Progress | 2025-11-10
|  | SB3/US27/T2 | HM: Create list of "trigger keywords" (gender, age). | HM | In Progress | 2025-11-10
|  | SB3/US27/T3 | HM: Write prototype function to check question for triggers. | HM | In Progress | 2025-11-10
|  | SB3/US27/T4 | CY: Discuss running this bias check on backend. | CY | In Progress | 2025-11-10
SB3/US28 | As a dev, I want to design the "Bias Alert" UI. | SB3/US28/T1 | CJ: Design "Personal Guardian" popup modal. | CJ | Not Started | 2025-11-11
|  | SB3/US28/T2 | CJ: Add placeholders for "Why it's unfair" & "Response." | CJ | Not Started | 2025-11-11
|  | SB3/US28/T3 | CJ: Show modal on (test) WebSocket event. | CJ | Not Started | 2025-11-11
|  | SB3/US28/T4 | HM: Create test button to trigger modal. | HM | Not Started | 2025-11-11
SB3/US29 | As a team, I want to clean up code and remove test elements. | SB3/US29/T1 | CJ: Remove temporary test buttons from UI. | CJ | Not Started | 2025-11-12
|  | SB3/US29/T2 | CY: Remove console.log statements from backend. | CY | Not Started | 2025-11-12
|  | SB3/US29/T3 | HM: Clean up and comment all prototype functions. | HM | Not Started | 2025-11-12
|  | SB3/US29/T4 | All: Conduct final code review for Sprint 3. | HM+CY+CJ | Not Started | 2025-11-12
SB3/US30 | As a team, I want to hold a retro for Sprint 2 and plan Sprint 4. | SB3/US30/T1 | CY: Facilitate Sprint 2 retrospective meeting. | CY | Not Started | 2025-11-12
|  | SB3/US30/T2 | HM: Document action items from retro. | HM | Not Started | 2025-11-12
|  | SB3/US30/T3 | CJ: Lead Sprint 4 feature brainstorming. | CJ | Not Started | 2025-11-12
|  | SB3/US30/T4 | All: Approve Sprint 3 work and Sprint 4 goals. | HM+CY+CJ | Not Started | 2025-11-12

## SB BD Ch03
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2025-09-25 | 4 | 0 | Tasks
2025-09-26 | 4 | 0
2025-09-27 | 4 | 0
2025-09-28 | 4 | 0
2025-09-29 | 4 | 0
2025-09-30 | 4 | 0
2025-10-01 | 4 | 0
2025-10-02 | 4 | 0
2025-10-03 | 4 | 0
2025-10-06 | 4 | 0
2025-10-07 | 4 | 0 |  | Days
2025-10-08 | 4 | 0
2025-10-09 | 4 | 0
2025-10-10 | 4 | 0
2025-10-13 | 4 | 0
2025-10-14 | 4 | 0
2025-10-15 | 4 | 0
2025-10-24 | 4 | 0
2025-10-27 | 4 | 0
2025-10-28 | 4 | 0
2025-10-29 | 4 | 2
2025-10-30 | 4 | 2
2025-10-31 | 4 | 2
2025-11-03 | 4 | 2
2025-11-04 | 4 | 2
2025-11-05 | 4 | 2
2025-11-06 | 4 | 2
2025-11-07 | 4 | 2
2025-11-10 | 4 | 2
2025-11-11 | 4 | 4
2025-11-12 | 8 | 8