## Sprint Backlog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <JobMirror>
SB2/US1 | As a Student, I want to make the basic Home Page of the project. | SB2/US1/T1 | CJ to build the initial UI layout for the Home Page with placeholder content. | CJ | Completed | 2025-08-16
|  | SB2/US1/T2 | HM to review the React component structure for the page. | HM | Completed | 2025-08-17
|  | SB2/US1/T3 | CY to set up the basic routing for the Home Page in the main application file. | CY | Completed | 2025-08-17
|  | SB2/US1/T4 | All members to do a final check to ensure the static Home Page renders correctly. | HM+CY+CJ | Completed | 2025-08-18
SB2/US2 | As a Student, I want to design the basic Login Page. | SB2/US2/T1 | CJ to create the initial layout and static input fields for the Login Page. | CJ | Completed | 2025-08-18
|  | SB2/US2/T2 | HM to review the initial design for clarity and user-friendliness. | HM | Completed | 2025-08-18
|  | SB2/US2/T3 | CY to provide feedback on the styling and consistency with the project theme. | CY | Completed | 2025-08-18
|  | SB2/US2/T4 | All members to approve the initial static design of the Login Page. | HM+CY+CJ | Completed | 2025-08-18
SB2/US3 | As a Student, I want to design the basic Sign Up Page. | SB2/US3/T1 | CJ to create the initial layout and static input fields for the Sign Up Page. | CJ | Completed | 2025-08-19
|  | SB2/US3/T2 | HM to review the design for any missing fields or information. | HM | Completed | 2025-08-19
|  | SB2/US3/T3 | CY to ensure the styling is consistent with the Login Page design. | CY | Completed | 2025-08-19
|  | SB2/US3/T4 | All members to approve the initial static design of the Sign Up Page. | HM+CY+CJ | Completed | 2025-08-19
SB2/US4 | As a Student, I want to make the server-side APIs for Authentication. | SB2/US4/T1 | CY to create the '/signup' and '/login' routes in the Node.js backend. | CY | Completed | 2025-08-20
|  | SB2/US4/T2 | HM to write the logic that connects these routes to Firebase Authentication. | HM | Completed | 2025-08-20
|  | SB2/US4/T3 | CJ to test both API endpoints using Postman to confirm they work as expected. | CJ | Completed | 2025-08-21
|  | SB2/US4/T4 | All members to review the backend authentication code together for correctness. | HM+CY+CJ | Completed | 2025-08-21
SB2/US5 | As a Student, I want to connect the Sign Up page to the backend. | SB2/US5/T1 | CJ to connect the Sign Up form's 'submit' action to the backend API. | CJ | Completed | 2025-08-22
|  | SB2/US5/T2 | CY to monitor the backend server for any errors during the API call. | CY | Completed | 2025-08-22
|  | SB2/US5/T3 | HM to check the Firebase console to confirm that a new user is created. | HM | Completed | 2025-08-22
|  | SB2/US5/T4 | All members to test the complete end-to-end signup process together. | HM+CY+CJ | Completed | 2025-08-22
SB2/US6 | As an ML Engineer, I want to complete my 'Intro to NLP' certification. | SB2/US6/T1 | HM to study all remaining course materials for the NLP certification. | HM | Completed | 2025-08-25
|  | SB2/US6/T2 | HM to take and pass the final certification exam. | HM | Completed | 2025-08-25
|  | SB2/US6/T3 | HM to share the certificate with the team for project documentation. | HM | Completed | 2025-08-25
|  | SB2/US6/T4 | HM to give a brief presentation to CJ and CY on key concepts learned. | HM+CY+CJ | Completed | 2025-08-25
SB2/US7 | As a Student, I want to design the basic Student Dashboard Home Page. | SB2/US7/T1 | CJ to create the initial layout of the dashboard page with placeholder sections. | CJ | Completed | 2025-08-26
|  | SB2/US7/T2 | HM to add a placeholder for where the "Past Interviews" list will be displayed. | HM | Completed | 2025-08-26
|  | SB2/US7/T3 | CY to add a static "Start New Interview" button to the layout. | CY | Completed | 2025-08-26
|  | SB2/US7/T4 | All members to review the initial dashboard layout together. | HM+CY+CJ | Completed | 2025-08-26
SB2/US8 | As a Student, I want to enhance the Login Page with functionality. | SB2/US8/T1 | CJ to connect the Login form's 'submit' action to the backend API. | CJ | Completed | 2025-08-27
|  | SB2/US8/T2 | HM to implement the logic to handle and display login error messages on the UI. | HM | Completed | 2025-08-27
|  | SB2/US8/T3 | CY to ensure the backend returns the correct success or error responses. | CY | Completed | 2025-08-27
|  | SB2/US8/T4 | All members to test the login flow with both correct and incorrect details. | HM+CY+CJ | Completed | 2025-08-27
SB2/US9 | As a Student, I want to define the different routes for the user. | SB2/US9/T1 | CJ to set up the main routes in React Router (e.g., /login, /dashboard). | CJ | Completed | 2025-08-28
|  | SB2/US9/T2 | CY to implement the protected route logic for pages like the dashboard. | CY | Completed | 2025-08-28
|  | SB2/US9/T3 | HM to test that all navigation links and redirects work as expected. | HM | Completed | 2025-08-28
|  | SB2/US9/T4 | All members to confirm the final routing logic is correct. | HM+CY+CJ | Completed | 2025-08-28
SB2/US10 | As a Student, I want to design the basic Live Interview page. | SB2/US10/T1 | CJ to create the initial UI structure for the Live Interview page. | CJ | Completed | 2025-08-29
|  | SB2/US10/T2 | HM to add a placeholder box for the 3D interviewer's view. | HM | Completed | 2025-08-29
|  | SB2/US10/T3 | CY to add a placeholder box for the user's webcam feed view. | CY | Completed | 2025-08-29
|  | SB2/US10/T4 | All members to review the static layout for balance and clarity. | HM+CY+CJ | Completed | 2025-08-29
SB2/US11 | As a Student, I want to enhance the Home Page by adding a Navbar. | SB2/US11/T1 | CJ to build a reusable Navbar component with the project logo and links. | CJ | Completed | 2025-08-30
|  | SB2/US11/T2 | HM to review the Navbar component's code for reusability. | HM | Completed | 2025-08-30
|  | SB2/US11/T3 | CY to integrate the Navbar component into the main application layout. | CY | Completed | 2025-08-31
|  | SB2/US11/T4 | All members to test the Navbar on all pages to ensure it works consistently. | HM+CY+CJ | Completed | 2025-08-31
SB2/US12 | As a Student, I want to make the server API for listing past interviews. | SB2/US12/T1 | HM to create the '/api/sessions' endpoint in the backend code. | HM | Not Started | 2025-09-01
|  | SB2/US12/T2 | CY to write the database query to fetch all sessions for the current user. | CY | Not Started | 2025-09-01
|  | SB2/US12/T3 | CJ to test the API with Postman to ensure it returns the correct data. | CJ | Not Started | 2025-09-02
|  | SB2/US12/T4 | All members to review the API code together for correctness. | HM+CY+CJ | Not Started | 2025-09-02
SB2/US13 | As a Student, I want to test the past interviews API and fix bugs. | SB2/US13/T1 | HM to test the '/api/sessions' endpoint with multiple different user accounts. | HM | Not Started | 2025-09-03
|  | SB2/US13/T2 | CY to fix any bugs found where one user's data might be visible to another. | CY | Not Started | 2025-09-03
|  | SB2/US13/T3 | CJ to help document the testing process and the bugs that were fixed. | CJ | Not Started | 2025-09-03
|  | SB2/US13/T4 | All members to confirm that the security fixes are working as intended. | HM+CY+CJ | Not Started | 2025-09-03
SB2/US14 | As a Student, I want to design the basic Feedback Report page. | SB2/US14/T1 | CJ to create the initial layout for the Feedback Report page. | CJ | Completed | 2025-09-04
|  | SB2/US14/T2 | HM to add placeholder sections for the main scores and metrics. | HM | Completed | 2025-09-04
|  | SB2/US14/T3 | CY to add a placeholder area for the list of interview questions and answers. | CY | Completed | 2025-09-04
|  | SB2/US14/T4 | All members to review and approve the initial design of the report page. | HM+CY+CJ | Completed | 2025-09-04
SB2/US15 | As a Student, I want to make the backend API for the report page. | SB2/US15/T1 | HM to create the '/api/report/:id' endpoint in the backend. | HM | Completed | 2025-09-05
|  | SB2/US15/T2 | CY to write the database query to fetch the data for a specific report ID. | CY | Completed | 2025-09-05
|  | SB2/US15/T3 | CJ to test the API with Postman using a sample report ID. | CJ | Completed | 2025-09-05
|  | SB2/US15/T4 | All members to review the API code for the report page together. | HM+CY+CJ | Completed | 2025-09-05
SB2/US16 | As a Student, I want to integrate functionality into the dashboard to show real data. | SB2/US16/T1 | CJ to connect the dashboard to the '/api/sessions' endpoint. | CJ | Completed | 2025-09-06
|  | SB2/US16/T2 | HM to implement the logic to display the fetched interview data using a Card component. | HM | Completed | 2025-09-06
|  | SB2/US16/T3 | CY to help debug any issues with the data flow from backend to frontend. | CY | Completed | 2025-09-06
|  | SB2/US16/T4 | All members to test the dashboard to ensure past interview data is shown correctly. | HM+CY+CJ | Completed | 2025-09-06
SB2/US17 | As a Student, I want to enhance the dashboard with a search bar. | SB2/US17/T1 | CJ to add a search input field to the dashboard UI. | CJ | Completed | 2025-09-07
|  | SB2/US17/T2 | HM to create the backend API route for searching interviews. | HM | Completed | 2025-09-07
|  | SB2/US17/T3 | CY to write the database logic to filter the interviews based on a search term. | CY | Completed | 2025-09-08
|  | SB2/US17/T4 | All members to test the search functionality on the dashboard. | HM+CY+CJ | Completed | 2025-09-08
SB2/US18 | As a Student, I want to improve the Login page with better user feedback. | SB2/US18/T1 | CJ to add a loading spinner that shows when the user clicks 'Login'. | CJ | Completed | 2025-09-09
|  | SB2/US18/T2 | HM to implement clear error messages for "User not found" or "Wrong password". | HM | Completed | 2025-09-09
|  | SB2/US18/T3 | CY to review the backend API to ensure it sends back clear error codes. | CY | Completed | 2025-09-09
|  | SB2/US18/T4 | All members to test the improved login feedback together. | HM+CY+CJ | Completed | 2025-09-09
SB2/US19 | As a Student, I want to implement the basic 3D scene for the interviewer. | SB2/US19/T1 | CJ to set up the Three.js scene, camera, and renderer in a React component. | CJ | In Progress | 2025-09-10
|  | SB2/US19/T2 | HM to add basic lighting to the 3D scene. | HM | In Progress | 2025-09-10
|  | SB2/US19/T3 | CY to help debug any issues with the scene rendering on the page. | CY | In Progress | 2025-09-10
|  | SB2/US19/T4 | All members to confirm that a simple 3D cube renders correctly. | HM+CY+CJ | In Progress | 2025-09-10
SB2/US20 | As a Student, I want to implement the webcam feed on the interview page. | SB2/US20/T1 | CJ to install and configure the 'react-webcam' library. | CJ | In Progress | 2025-09-11
|  | SB2/US20/T2 | HM to implement the logic to request camera permission from the user. | HM | In Progress | 2025-09-11
|  | SB2/US20/T3 | CY to help style and position the webcam feed component on the page. | CY | In Progress | 2025-09-11
|  | SB2/US20/T4 | All members to test the webcam functionality on different browsers. | HM+CY+CJ | In Progress | 2025-09-11
SB2/US21 | As a Student, I want to create a question bank for the interviews. | SB2/US21/T1 | HM, CY, and CJ to each research and contribute 10 common interview questions. | HM+CY+CJ | Completed | 2025-09-12
|  | SB2/US21/T2 | HM to compile all questions into a single list and remove any duplicates. | HM | Completed | 2025-09-12
|  | SB2/US21/T3 | CY to create a JSON file in the backend project to store the final question bank. | CY | Completed | 2025-09-12
|  | SB2/US21/T4 | CJ to review the final JSON file for any formatting errors or typos. | CJ | Completed | 2025-09-12
SB2/US22 | As a Student, I want to create an API to get a random question from the bank. | SB2/US22/T1 | HM to create the '/api/questions/random' endpoint in the backend code. | HM | Completed | 2025-09-13
|  | SB2/US22/T2 | CY to write the logic to read the question bank JSON file and select one randomly. | CY | Completed | 2025-09-13
|  | SB2/US22/T3 | CJ to test the endpoint multiple times with Postman to ensure it works. | CJ | Completed | 2025-09-13
|  | SB2/US22/T4 | All members to review the code for the random question API together. | HM+CY+CJ | Completed | 2025-09-13
SB2/US23 | As a Student, I want to display the first question on the interview page. | SB2/US23/T1 | CJ to write the frontend code to call the random question API when the page loads. | CJ | In Progress | 2025-09-14
|  | SB2/US23/T2 | HM to implement the logic to display the fetched question text in the UI. | HM | In Progress | 2025-09-14
|  | SB2/US23/T3 | CY to help style the question display area to make it look clean. | CY | In Progress | 2025-09-14
|  | SB2/US23/T4 | All members to test that a question appears correctly on the page. | HM+CY+CJ | In Progress | 2025-09-14
SB2/US24 | As a Backend Developer, I want to complete my 'Intro to AI' certification. | SB2/US24/T1 | CY to study all remaining course materials for the AI certification. | CY | Completed | 2025-09-15
|  | SB2/US24/T2 | CY to take and pass the final certification exam. | CY | Completed | 2025-09-15
|  | SB2/US24/T3 | CY to share the certificate with the team for project documentation. | CY | Completed | 2025-09-15
|  | SB2/US24/T4 | CY to give a brief presentation to HM and CJ on what was learned. | HM+CY+CJ | Completed | 2025-09-15
SB2/US25 | As a Frontend Developer, I want to work towards my 'Basic of React JS' certification. | SB2/US25/T1 | CJ to review the remaining course materials for the certification. | CJ | Completed | 2025-09-15
|  | SB2/US25/T2 | HM and CY to help CJ by reviewing his practice coding exercises. | HM+CY | Completed | 2025-09-15
|  | SB2/US25/T3 | CJ to prepare for the final exam scheduled for after the sprint (Sept 19). | CJ | Completed | 2025-09-15
|  | SB2/S25/T4 | All members to hold a quick Q&A session to help CJ prepare. | HM+CY+CJ | Completed | 2025-09-15
SB2/US26 | As a Student, I want to enhance the Navbar with a Logout feature. | SB2/US26/T1 | CJ to add a "Logout" button to the Navbar component. | CJ | Completed | 2025-09-15
|  | SB2/US26/T2 | CY to implement the Firebase logout functionality in the backend. | CY | Completed | 2025-09-15
|  | SB2/US26/T3 | HM to connect the frontend button to the backend logout logic. | HM | Completed | 2025-09-15
|  | SB2/US26/T4 | All members to test the logout feature to ensure it works correctly. | HM+CY+CJ | Completed | 2025-09-15
SB2/US27 | As a Student, I want to improve the Dashboard by showing a "Loading" state. | SB2/US27/T1 | CJ to add a loading spinner component to the dashboard page. | CJ | Not Started | 2025-09-15
|  | SB2/US27/T2 | HM to implement the logic to show the spinner while data is being fetched. | HM | Not Started | 2025-09-15
|  | SB2/US27/T3 | CY to review the implementation for any potential bugs. | CY | Not Started | 2025-09-15
|  | SB2/US27/T4 | All members to test the loading state on the dashboard. | HM+CY+CJ | Not Started | 2025-09-15
SB2/US28 | As a Student, I want to create a simple "About Us" page. | SB2/US28/T1 | CJ to create the basic layout for the "About Us" page. | CJ | Completed | 2025-09-15
|  | SB2/US28/T2 | HM to write a short paragraph about the project's mission. | HM | Completed | 2025-09-15
|  | SB2/US28/T3 | CY to add the names of the team members to the page. | CY | Completed | 2025-09-15
|  | SB2/US28/T4 | All members to review the content and design of the page. | HM+CY+CJ | Completed | 2025-09-15
SB2/US29 | As a Student, I want to create a basic Footer component for the application. | SB2/US29/T1 | CJ to design the layout for the application footer. | CJ | Completed | 2025-09-15
|  | SB2/US29/T2 | HM to add links to pages like "About Us". | HM | Completed | 2025-09-15
|  | SB2/US29/T3 | CY to add project branding and copyright information. | CY | Completed | 2025-09-15
|  | SB2/US29/T4 | All members to ensure the footer is displayed correctly on all pages. | HM+CY+CJ | Completed | 2025-09-15
SB2/US30 | As a Student, I want to conduct a Sprint Retrospective for Sprint 1. | SB2/US30/T1 | CY to facilitate a meeting to discuss what went well in Sprint 1. | CY | Completed | 2025-09-15
|  | SB2/US30/T2 | HM to lead the discussion on what could be improved for the next sprint. | HM | Completed | 2025-09-15
|  | SB2/US30/T3 | CJ to help formally agree on the action items for Sprint 3. | CJ | Completed | 2025-09-15
|  | SB2/US30/T4 | All members to contribute to documenting the retrospective notes. | HM+CY+CJ | Completed | 2025-09-15

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2025-08-16 | 1 | 0 | Tasks
2025-08-17 | 2 | 0
2025-08-18 | 5 | 0
2025-08-19 | 4 | 0
2025-08-20 | 4 | 0
2025-08-21 | 4 | 0
2025-08-22 | 4 | 0
2025-08-23 | 4 | 0
2025-08-25 | 4 | 0
2025-08-26 | 4 | 0
2025-08-27 | 4 | 0 |  | Days
2025-08-28 | 4 | 0
2025-08-29 | 4 | 0
2025-08-30 | 4 | 0
2025-08-31 | 4 | 0
2025-09-01 | 4 | 4
2025-09-02 | 4 | 4
2025-09-03 | 4 | 4
2025-09-04 | 4 | 0
2025-09-05 | 4 | 0
2025-09-06 | 4 | 0
2025-09-07 | 2 | 0
2025-09-08 | 4 | 0
2025-09-09 | 4 | 0
2025-09-10 | 4 | 2
2025-09-11 | 4 | 2
2025-09-12 | 4 | 0
2025-09-13 | 4 | 0
2025-09-14 | 4 | 3
2025-09-15 | 16 | 6