## Product Backlog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT |  |  |  |  | Student Name | Code
1 | SB1/US1 | Student | Form a team of 3 members | I can complete the project on time. | 1 | CY | 2025-07-15 |  | Chanchal Yaduvanshi | CY
1 | SB1/US2 | Student | Finalize the Project Idea | I can submit the project idea to the project coordinator. | 1 | CY | 2025-07-16 |  | Harsh Mandhana | HM
1 | SB1/US3 | Student | Fill the project submission form | the faculty can review and approve our project idea. | 1 | CJ | 2025-07-18 |  | Chirag Jain | CJ
1 | SB1/US4 | Student | prepare for the project idea defense | we can get our project idea approved. | 1 | HM | 2025-07-20
1 | SB1/US5 | Student | Present our project idea to the faculty | we can get it approved. | 1 | CY | 2025-07-22
1 | SB1/US6 | Student | Access the Final Year Project Google Classroom | I can access all official materials. | 1 | HM | 2025-07-24
1 | SB1/US7 | Student | Divide the high-level work among team members | everyone knows their core responsibilities. | 1 | CY | 2025-07-25
1 | SB1/US8 | Student | Decide the official title and branding for the project | we can create a logo and theme. | 1 | CJ | 2025-07-28
1 | SB1/US9 | Student | Conduct a competitor analysis | we understand the market. | 1 | CY | 2025-07-29
1 | SB1/US10 | Student | Define the target user personas for our project | we can build a user-centric application. | 1 | CY | 2025-07-30
1 | SB1/US11 | Student | Define the Minimum Viable Product (MVP) feature list | we can prioritize our work. | 1 | HM | 2025-08-01
1 | SB1/US12 | Student | Research and understand Web-based AR technologies | we can choose the right tool for the AI interviewer. | 1 | CJ | 2025-08-02
1 | SB1/US13 | Student | Research Body Language Tracking technologies | we understand how to analyze the user's video. | 1 | HM | 2025-08-04
1 | SB1/US14 | Student | Research Speech-to-Text technologies | we can convert the user's answers to text. | 1 | CY | 2025-08-05
1 | SB1/US15 | Student | Research Voice Analysis technologies | we know how to measure confidence and pace. | 1 | HM | 2025-08-06
1 | SB1/US16 | Student | Research Dynamic Question Generation technologies | the AI interviewer can ask follow-up questions. | 1 | HM | 2025-08-07
1 | SB1/US17 | Student | Research Text-to-Speech technologies | the AI interviewer can speak the questions. | 1 | CJ | 2025-08-08
1 | SB1/US18 | Student | Research and select a Frontend UI Framework | we can build the UI efficiently. | 1 | CJ | 2025-08-09
1 | SB1/US19 | Student | Research Backend and Database options | we choose the best tools for our server. | 1 | CY | 2025-08-11
1 | SB1/US20 | Student | Finalize the complete technology stack for the project | we have a clear plan for development. | 1 | CY | 2025-08-12
1 | SB1/US21 | Student | Create a high-level system architecture diagram | we understand how all parts of the system connect. | 1 | HM | 2025-08-13
1 | SB1/US22 | Student | Create the initial UI wireframes for the application | we have a visual guide for the UI. | 1 | CJ | 2025-08-14
1 | SB1/US23 | Student | Learn the basics of React.js | the team can work effectively on the frontend. | 1 | CJ | 2025-08-14
1 | SB1/US24 | Student | Learn the basics of Node.js | the team can build the backend API. | 1 | CY | 2025-08-15
1 | SB1/US25 | Student | Learn the basics of MediaPipe | we are prepared for the ML part of the project. | 1 | HM | 2025-08-15
1 | SB1/US26 | Student | Set up the project management board | we can track our progress visually. | 1 | CY | 2025-08-15
1 | SB1/US27 | Student | Start working on the project synopsis | we can submit the first part of our documentation. | 1 | CY | 2025-08-15
1 | SB1/US28 | Student | Define the project's folder structure in GitHub | our code will be organized and easy to find. | 1 | CY | 2025-08-15
1 | SB1/US29 | Student | Create the initial Product Backlog document | we can plan all the project's features. | 1 | CY | 2025-08-15
1 | SB1/US30 | Student | Create the Sprint Backlog 1 document | we can track the tasks for the first sprint. | 1 | CJ | 2025-08-15
2 | SB2/US1 | Student | Make the basic Home Page of the project | we can add more functionality to it. | 2 | CJ | 2025-08-18
2 | SB2/US2 | Student | Design the basic Login Page | users have a way to enter the application. | 2 | CJ | 2025-08-18
2 | SB2/US3 | Student | Design the basic Sign Up Page | new users can register for the application. | 2 | CJ | 2025-08-19
2 | SB2/US4 | Student | Make the server-side APIs for Authentication | we can securely manage users. | 2 | CY | 2025-08-21
2 | SB2/US5 | Student | Connect the Sign Up page to the backend | users can actually create an account. | 2 | CJ | 2025-08-22
2 | SB2/US6 | Student | Complete my 'Intro to NLP' certification | I am prepared for the ML tasks. | 2 | HM | 2025-08-25
2 | SB2/US7 | Student | Design the basic Student Dashboard Home Page | logged-in users have a landing page. | 2 | CJ | 2025-08-26
2 | SB2/US8 | Student | Enhance the Login Page with functionality | users can sign in to their accounts. | 2 | CJ | 2025-08-27
2 | SB2/US9 | Student | Define the different routes for the user | they can navigate the application. | 2 | CJ | 2025-08-28
2 | SB2/US10 | Student | Design the basic Live Interview page | we have a layout for the core feature. | 2 | CJ | 2025-08-29
2 | SB2/US11 | Student | Enhance the Home Page by adding a Navbar | users can navigate easily from any page. | 2 | CJ | 2025-08-31
2 | SB2/US12 | Student | Make the server API for listing past interviews | we can show users their history. | 2 | HM | 2025-09-02
2 | SB2/US13 | Student | Test the past interviews API and fix bugs | the data is secure and correct. | 2 | HM | 2025-09-03
2 | SB2/US14 | Student | Design the basic Feedback Report page | users have a place to see their results. | 2 | CJ | 2025-09-04
2 | SB2/US15 | Student | Make the backend API for the report page | we can fetch the data for a specific report. | 2 | HM | 2025-09-05
2 | SB2/US16 | Student | Integrate functionality into the dashboard to show real data | the dashboard is useful and not just static. | 2 | CJ | 2025-09-06
2 | SB2/US17 | Student | Enhance the dashboard with a search bar | users can easily find past interviews. | 2 | CJ | 2025-09-08
2 | SB2/US18 | Student | Improve the Login page with better user feedback | the user experience is smoother. | 2 | CJ | 2025-09-09
2 | SB2/US19 | Student | Implement the basic 3D scene for the interviewer | we have the foundation for the AR feature. | 2 | CJ | 2025-09-10
2 | SB2/US20 | Student | Implement the webcam feed on the interview page | we can capture the user's video for analysis. | 2 | CJ | 2025-09-11
2 | SB2/US21 | Student | Create a question bank for the interviews | the AI has questions to ask the user. | 2 | HM | 2025-09-12
2 | SB2/US22 | Student | Create an API to get a random question from the bank | the interview can be dynamic. | 2 | HM | 2025-09-13
2 | SB2/US23 | Student | Display the first question on the interview page | the user knows what to answer. | 2 | CJ | 2025-09-14
2 | SB2/US24 | Student | Complete my 'Intro to AI' certification | I have the required foundational knowledge. | 2 | CY | 2025-09-15
2 | SB2/US25 | Student | Work towards my 'Basic of React JS' certification | I have the required frontend skills. | 2 | CJ | 2025-09-15
2 | SB2/US26 | Student | Enhance the Navbar with a Logout feature | users can securely sign out of their account. | 2 | CJ | 2025-09-15
2 | SB2/US27 | Student | Improve the Dashboard by showing a "Loading" state | the UI feels more responsive to the user. | 2 | CJ | 2025-09-15
2 | SB2/US28 | Student | Create a simple "About Us" page | users can learn more about the project and team. | 2 | CJ | 2025-09-15
2 | SB2/US29 | Student | Create a basic Footer component for the application | every page has a consistent look and feel. | 2 | CJ | 2025-09-15
2 | SB2/US30 | Student | Conduct a Sprint Retrospective for Sprint 1 | we can improve our process for the next sprint. | 2 | CY | 2025-09-15
3 | SB3/US1 | Student | Implement the live webcam feed on the interview page | we can capture the user's video for analysis. | 3 | CJ | 2025-09-25
3 | SB3/US2 | Student | Implement the basic 3D scene for the interviewer | we have the foundation for the AR feature. | 3 | CJ | 2025-09-26
3 | SB3/US3 | Student | Display the first question on the interview page | the user knows what to answer. | 3 | CJ | 2025-09-29
3 | SB3/US4 | Student | Implement session control buttons (Start, Pause, End) | users can manage their interview session. | 3 | CJ | 2025-09-30
3 | SB3/US5 | Student | Make the server API for starting an interview session | we can create a new session record in the database. | 3 | CY | 2025-10-01
3 | SB3/US6 | Student | Make the server API for ending an interview session | we can update the session record with an end time. | 3 | CY | 2025-10-02
3 | SB3/US7 | Student | Set up the MediaPipe library in the project | we are prepared to prototype body language analysis. | 3 | HM | 2025-10-03
3 | SB3/US8 | Student | Set up the Web Speech API for transcription | we are prepared to prototype speech-to-text. | 3 | HM | 2025-10-06
3 | SB3/US9 | Student | Implement Text-to-Speech (TTS) for the 3D avatar | the AI interviewer can speak the questions aloud. | 3 | HM | 2025-10-07
3 | SB3/US10 | Student | Improve the interview page with a "Loading" state | the UI feels more responsive to the user. | 3 | CJ | 2025-10-08
3 | SB3/US11 | Student | Implement redirect to Feedback Report on session end | users can immediately see their results. | 3 | CJ | 2025-10-09
3 | SB3/US12 | Student | Design the placeholder for the Confidence Score | users have a place to see this key metric. | 3 | CJ | 2025-10-10
3 | SB3/US13 | Student | Design the "Body Language" section of the report | users have a place to see this feedback. | 3 | CJ | 2025-10-13
3 | SB3/US14 | Student | Design the "Voice Analysis" section of the report | users have a place to see this feedback. | 3 | CJ | 2025-10-14
3 | SB3/US15 | Student | Design the Q&A list for the feedback report | users can review their transcribed answers. | 3 | CJ | 2025-10-15
3 | SB3/US16 | Student | Prototype the "slouch detection" logic | we can validate the real-time alert concept. | 3 | HM | 2025-10-24
3 | SB3/US17 | Student | Prototype the "filler word" counting logic | we can validate the voice analysis concept. | 3 | HM | 2025-10-27
3 | SB3/US18 | Student | Implement a basic WebSocket server | we have a foundation for real-time communication. | 3 | CY | 2025-10-28
3 | SB3/US19 | Student | Connect the slouch detection prototype to the UI via WebSockets | we can test the real-time alert. | 3 | HM | 2025-10-29
3 | SB3/US20 | Student | Implement the "Select Interview Type" modal | users can choose their practice mode. | 3 | CJ | 2025-10-30
3 | SB3/US21 | Student | Enhance the question API to filter by type | the interview can be dynamic and relevant. | 3 | CY | 2025-10-31
3 | SB3/US22 | Student | Design the placeholder for the Technical Whiteboard | we have a layout for the technical interview feature. | 3 | CJ | 2025-11-03
3 | SB3/US23 | Student | Integrate functionality into the dashboard to show real data | the dashboard is useful and not just static. | 3 | CJ | 2025-11-04
3 | SB3/US24 | Student | Enable navigation from Dashboard to Feedback Report | users can click a past interview to see its results. | 3 | CJ | 2025-11-05
3 | SB3/US25 | Student | Refine the "About Us" page | users can learn more about the project and team. | 3 | CJ | 2025-11-06
3 | SB3/US26 | Student | Refine the basic Footer component | every page has a consistent look and feel. | 3 | CJ | 2025-11-07
3 | SB3/US27 | Student | Research Bias Detection technologies | we can define the scope for the bias alert feature. | 3 | HM | 2025-11-10
3 | SB3/US28 | Student | Design the "Bias Alert" (Guardian) popup | we have a layout for this key feature. | 3 | CJ | 2025-11-11
3 | SB3/US29 | Student | Refactor and clean up Sprint 3 code | the codebase is stable for the next sprint. | 3 | CY | 2025-11-12
3 | SB3/US30 | Student | Conduct a Sprint Retrospective for Sprint 2 | we can improve our process for the next sprint. | 3 | CY | 2025-11-12